## Sprint i
ID | User Story | Story Tasks | Sprint Number | Sprint Goal | Story Type | Story Points | Story Points Completed | Names and Contribution Percentage
N1 | As a neurodivergent user, I want the app to be designed with people like me in mind so that I will be able to navigate it with minimal issue |  | 1 | Deliverable 1 user storys | unassigned | 5 | 0 | not completed
N2 | (As a neurodivergent user, I want the app’s generative AI assistance to be effective and tested to guarantee it will be received positively by the recipient) |  | 1 | Deliverable 1 user storys | unassigned | 8 | 0 | not completed
N3 | As a neurodiverse student, I would like this app to help me work on social skills in the workplace. |  | 1 | Deliverable 1 user storys | unassigned | 7 | 0 | not completed
N4 | As a neurodiverse student, I would like this app to help me prepare for job interviews. |  | 1 | Deliverable 1 user storys | unassigned | 6 | 0 | not completed
N5 | As a neurodiverse user, I would like the app to connect me with recruiters who are willing to work with my disabilities. |  | 1 | Deliverable 1 user storys | unassigned | 6 | 0 | not completed
L1 | As a low-income user, I want the app to suggest solutions and advice that are realistically applicable to my financial situation |  | 1 | Deliverable 1 user storys | unassigned | 6 | 0 | not completed
16 |  | Create UI Mockups | 1 | Deliverable 1 tasks | Dominic Huntington | 2 | 2 | Dominic Huntington 100%
17 |  | functional and non functional requirements | 1 | Deliverable 1 tasks | everybody | 2 | 2 | Cade Carr 20%, Dominic Huntington 20%, Ben Miller 20%, Jacob bryant 20%, Drew Marecek 20%
18 |  | rewrite user storys | 1 | Deliverable 0 rework | Drew Marecek | 2 | 2 | Drew Marecek 100%
19 |  | rewirite problem statements | 1 | Deliverable 0 rework | Jacob Bryant | 2 | 2 | Jacob Bryant 100%
20 |  | Complete SRS | 2 | Deliverable 2 tasks | Jacob Bryant, Dominic Huntington, Drew Marecek | 3 | 3 | Jacob Bryant 33%, Dominic Huntington 33%, Drew Marecek 33%
21 |  | Archetecture design | 2 | Deliverable 2 tasks | Dominic Huntington | 3 | 3 | Dominic Huntington
22 |  | Use Case Diagrams | 2 | Deliverable 2 tasks | Cade Carr, Ben Miller | 3 | 3 | Cade Carr 50%, Ben Miller 50%
23 |  | Use Case Model | 2 | Deliverable 2 tasks | Cade Carr, Ben Miller | 3 | 3 | Cade Carr 50%, Ben Miller 50%
24 |  | New version of Applicatio | 2 | Deliverable 2 tasks | Jacob Bryant | 4 | 4 | Jacob Bryant
25 |  | Domain Model | 3 | Deliverable 3 tasks | Cade Carr | 2 | 2 | Cade Carr 100%
26 |  | Create Site Login | 3 | Deliverable 3 tasks | Ben Miller | 2 | 2 | Ben Miller 100%
27 |  | Develop Test Cases | 3 | Deliverable 3 tasks | Jacob Bryant, Drew Marecek | 4 | 4 | Jacob Bryant 50%, Drew Marecek 50%
28 |  | Video Showcase | 3 | Deliverable 3 tasks | Jacob Bryant | 3 | 3 | Jacob Bryant 100%
29 |  | Login Test | 4 | Deliverable 4 tasks
30 |  | Job Listing | 4 | Delivarable 4 tasls | Ben Miller | 4 | 4 | Ben Miller 100%
31 |  | AI Integration | 4 | Deliverable 4 tasks | Jacob Bryant, Drew Marecek | 4 | 4 | Jacob Bryant 50%, Drew Marecek 50%
32 |  | Job Listing Test | 4 | Deliverable 4 tasks | Ben Miller | 3 | 3 | Ben Miller 100%
33 |  | Domain Model | 4 | Deliverable 4 tasks | Jacob Bryant | 4 | 4 | Jacob Bryant 100%
34 |  | UI Prototype | 4 | Deliverable 4 tasks | Dominic Huntington | 4 | 4 | Dominic Huntington 100%
35 |  | Moving Registration To Front End | 4 | Deliverable 4 tasks | Jacob Bryant | 4 | 4 | Jacob Bryant 100%
36 |  | Listing Window Mock Up | 5 | Deliverable 5 tasks | Dominic Huntington | 5 | 5 | Dominic Huntington 100%
37 |  | Apply to job | 5 | Deliverable 5 tasks | Jacob Bryant | 5 | 5 | Jacob Bryant 100%
38 |  | Request Mentorship | 5 | Deliverable 5 tasks | Ben Miller | 4 | 4 | Ben Miller 100%
39 |  | Fully Integrate AI Helper into chat box | 5 | Deliverable 5 tasks | Drew Marecek | 6 | 6 | Drew Marecek 100%
40 |  | Home Page Resources | 5 | Deliverable 5 tasks | Dominic Huntington | 4 | 4 | Dominic Huntington 100%
41 |  | AI WIndow Mockup | 5 | Deliverable 5 tasks | Dominic Huntington | 4 | 4 | Dominic Huntington 100%
42 |  | Add Sorting Controls to Listing Page | 5 | Deliverable 5 tasks | Jacob Bryant | 5 | 5 | Jacob Bryant 100%

## Column Description
o Sprint Goal and Number. o Story copied from the project backlog or a sprint task story. o Story Type: F (functional), NF (non-functional) with a subtype: B (bug), T (technical work), KA(knowledge acquisition, technical or design/users). o Story Points. o Story Points Completed. o Team Member Names and percentage of contribution to the story.
Note there is another option this year to export this document instead from Github projects, see https://discord.com/channels/1280324227790278737/1280324228255711263/1291882302460399657