## Sheet1
ID | User Story | Sprint Number | Story Priority | Story Status | Story Points (see comment)
A-1 | As a neurodivergent user, I want the app to be designed with people like me in mind so that I will be able to navigate it with minimal issue | 1 | H | In Progress | 5
A-2 | (As a neurodivergent user, I want the app’s generative AI assistance to be effective and tested to guarantee it will be received positively by the recipient) | 1 | M | In Progress | 8
A-3 | As a neurodiverse student, I would like this app to help me work on social skills in the workplace. | 1 | L | In Progress | 7
A-4 | As a neurodiverse student, I would like this app to help me prepare for job interviews. | 1 | M | In Progress | 6
A-5 | As a neurodiverse user, I would like the app to connect me with recruiters who are willing to work with my disabilities. | 1 | H | In Progress | 6
A-6 | As a low-income user, I want the app to suggest solutions and advice that are realistically applicable to my financial situation | 2 | H | In Progress | 6
D-1 | As a low-income user, I want the apps generative AI to be capable of delivering text in the tone that was intended | 2 | M | In Progress | 8
A-7 | As a low-income user, I want the app to suggest possible free or affordable learning opportunities outside of college or classes I may not be able to afford | 2 | H | In Progress | 5
A-8 | As a lower-income student, I would like this app to help me find jobs to apply to in the tech field that don’t require me to have a top-of-the-line computer. | 2 | M | In Progress | 7
A-9 | As a lower-income student, I would like this app to help me find jobs in tech that are near public transportation. | 3 | M | In Progress | 6
A-10 | As a lower-income student, I would like this app to help me find mentors in tech so that I may connect with them and learn from their experiences. | 3 | H | In Progress | 5
A-11 | As a low-income student, I want an app that can connect me with tech mentors and can provide guidance to internships so that the process is clear and I can get a career in tech | 7+ | H | In Progress | 6
A-12 | As a user unfamiliar with the industry, I would like the app to introduce me to online assessments and suggest resources for me to become acquainted with them | 3 | M | In Progress | 5
A-13 | As a current computer science student who is struggling to pay rent, I want a place where I will be able to find jobs and connect with employers in my area so that I can give back to my community and build a successful career. | 4 | H | In Progress | 7
A-14 | As a student struggling to pay tuition, I want access to a free app that has job opportunities and people to get connected to so that I have a pathway into a job in tech and improve my economic situation. | 4 | H | In Progress | 6
A-15 | As a student, I would like the app to find positions near me that are flexible with my school schedule so that I can maintain a balance between classes and work. | 7+ | H | In Progress | 7
Note on E1: ====== ID#AAAAg7YSlfY Gregory Nelson (2022-10-10 22:25:40) Make these readable as whole words
Note on F1: ====== ID#AAABWwdAOUQ Gregory Nelson (2024-10-04 20:18:38) The basic idea is a story with 3 points is 3x the effort as a 1 point story, 2 points is 2x the effort, etc. In general without much experience it's hard for you to estimate relative feature sizes. Just do your best. Here's more information https://www.mountaingoatsoftware.com/blog/what-are-story-points