## Sprint i
ID | User Story | Story Tasks | Sprint Number | Sprint Goal | Story Type | Story Points | Story Points Completed | Names and Contribution Percentage
N1 | As a neurodivergent user, I want the app to be designed with people like me in mind so that I will be able to navigate it with minimal issue |  | 1 | Deliverable 1 user storys | unassigned | 5 | 0 | not completed
N2 | (As a neurodivergent user, I want the app’s generative AI assistance to be effective and tested to guarantee it will be received positively by the recipient) |  | 1 | Deliverable 1 user storys | unassigned | 8 | 0 | not completed
N3 | As a neurodiverse student, I would like this app to help me work on social skills in the workplace. |  | 1 | Deliverable 1 user storys | unassigned | 7 | 0 | not completed
N4 | As a neurodiverse student, I would like this app to help me prepare for job interviews. |  | 1 | Deliverable 1 user storys | unassigned | 6 | 0 | not completed
N5 | As a neurodiverse user, I would like the app to connect me with recruiters who are willing to work with my disabilities. |  | 1 | Deliverable 1 user storys | unassigned | 6 | 0 | not completed
L1 | As a low-income user, I want the app to suggest solutions and advice that are realistically applicable to my financial situation |  | 1 | Deliverable 1 user storys | unassigned | 6 | 0 | not completed
16 |  | Create UI Mockups | 1 | deliverable 1 tasks | Dominic Huntington | 2 | 2 | Dominic Huntington 100%
17 |  | functional and non functional requirements | 1 | deleverible 1 tasks | everybody | 2 | 2 | Cade Carr 20%, Dominic Huntington 20%, Ben Miller 20%, Jacob bryant 20%, Drew Marecek 20%
18 |  | rewrite user storys | 1 | deleverable 0 rework | Drew Marecek | 2 | 2 | Drew Marecek 100%
19 |  | rewirite problem statements | 1 | deleverable 0 rework | Jacob Bryant | 2 | 2 | Jacob Bryant 100%

## Column Description
o Sprint Goal and Number. o Story copied from the project backlog or a sprint task story. o Story Type: F (functional), NF (non-functional) with a subtype: B (bug), T (technical work), KA(knowledge acquisition, technical or design/users). o Story Points. o Story Points Completed. o Team Member Names and percentage of contribution to the story.
Note there is another option this year to export this document instead from Github projects, see https://discord.com/channels/1280324227790278737/1280324228255711263/1291882302460399657